## PMR
DENR-PENRO, CAPIZ | [11 empty] | Procurement Monitoring Report as of December 31, 2023
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
| Procurement of Office Supplies and materials, other supplies and Ict Supplies | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | Competitive Bidding | N/A | 12-05-2023 |  | 22-05-2023 | N/A | 2023-02-06 | -302 | 07-06-2023 | 07-06-2023 | 20-06-2023 | 150 |  |  | 20-06-2023 | N/A | 03-07-2023 |  | -273 | 17-08-2023 | 17-08-2023 | Government of the Philippines (current year's budget) | 818656.75 | 818656.75 |  | 624915.5 | 624915.5 |  | 0.23666 | Dale Bernas Danilo So Chan Resident Auditor | N/A | N/A | 30-05-2023 | 30-05-2023 | 30-05-2023 | N/A | Completed | FALSE | FALSE
| Procurement of electrical supplies for installation of airconditioning unit at the holding area and for extension installation from generator set to server room and hostel room for official use of Office of the PENRO of the DENR PENRO Capiz | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 24-07-2023 |  |  |  | 24-07-2023 | N/A | 26-07-2023 |  |  | 28-07-2023 | 31-07-2023 | Government of the Philippines (current year's budget) | 24000 | 24000 |  | 22975 | 22975 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
| Catering Services and accommodation for the condcut of Two (2) - day gabuc wetland Management Plan Updating Cum Training Workshop on August 17-18, 2023 | Nonilon Molina/SvEms, Chief, CDS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 24-07-2023 |  |  |  | 24-07-2023 | N/A | 28-07-2023 |  |  | 17&18-08-2023 | 18-08-2023 | Government of the Philippines (current year's budget) | 66800 | 66800 |  | 61840 | 61840 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Procurement of essential supplies | Cherry may Calderon/AO IV(HRMO II) | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 31-07-2023 |  |  |  | 31-07-2023 | N/A | 03-08-2023 |  |  | 13-09-2023 | 13-09-2023 | Government of the Philippines (current year's budget) | 82000 | 82000 |  | 68000 | 68000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Catering services on the Enterprise Development and Organizational Development of Identified People's Organizations: Biodiversity-Friendly Enterprise Enhancement Training | Jean Carla Ibañez/FT II/Chief, CRFMU | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 04-08-2023 |  |  |  | 04-08-2023 | N/A | 07-08-2023 |  |  | 08,09,10-08-2023 | 10-08-2023 | Government of the Philippines (current year's budget) | 162900 | 162900 |  | 144350 | 144350 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Procurement of ICT Equipment fror official use of Monitoring and Enforcement Section | Shirley Villasor/Forester III/Chief, MES | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 11-08-2023 |  |  |  | 11-08-2023 | N/A | 15-08-2023 |  |  | 13-09-2023 | 13-09-2023 | Government of the Philippines (current year's budget) | 79999 | 79999 |  | 66189 | 66189 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Procurement of ICT Equipment for official use of PENRO Capiz and CENRO Mambusao | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | 13-07-2023 |  | 21-07-2023 | N/A | 02-08-2023 |  | 02-08-2023 | 07-08-2023 | 11-08-2023 |  |  |  | 11-08-2023 | N/A | 17-08-2023 |  |  | 22-09-2023 | 22-09-2023 | Government of the Philippines (current year's budget) | 804400 | 804400 |  | 641671 | 205266 | 436405 |  | Dale Bernas Danilo So Chan Gloria Melba Joy C. Payofelin | N/A | N/A | 31-07-2023 | 31-07-2023 | 31-07-2023 | N/A | Completed
| Procurement of Semi-expendable ICT Equipment for official use of DENR PENRO Capiz | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 22-08-2023 |  |  |  | 22-08-2023 | N/A | 23-08-2023 |  |  | 21-09-2023 | 21-09-2023 | Government of the Philippines (current year's budget) | 49900 | 49900 |  | 49490 | 49490 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Conduct of Soil Analysis (available phosphorous (P), exchangable potassium (K), and total Nitrogen (N) for the implementation of CY 2024 ENGP Plantation | Marlyn Caraggayan/Forester I/NGP Coordinator | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 24-08-2023 |  |  |  | 24-08-2023 | N/A | 25-08-2023 |  |  |  |  | Government of the Philippines (current year's budget) | 120000 | 120000 |  | 100000 | 100000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Catering services for the condcut of 3rd PAMB meeting for CY 2023 of Panay River Watershed Forest Reserve (PRWFR) on September 8, 2023 | Gregoria Alenaje/OIC-Chief, CENR Officer | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 06-09-2023 |  |  |  | 06-09-2023 | N/A | 07-09-2023 |  |  | 08-09-2023 | 08-09-2023 | Government of the Philippines (current year's budget) | 20900 | 20900 |  | 20710 | 20710 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Catering services for the condcut of Provincial Planning Workshop for the preparation of FY 2024 GAD Work and Financial Plan based on National Expenditure Program (NEP) and Harmonized Gender and Development Guidelines/Tools (HGDG) Orientation on September 12-13, 2023 | Mary Grace Molina/PO II/OIC-Chief, Planning Section | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 11-09-2023 |  |  |  | 11-09-2023 | N/A | 11-09-2023 |  |  | 12,13-09-2023 | 13-09-2023 | Government of the Philippines (current year's budget) | 96360 | 96360 |  | 81180 | 81180 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Procurement of ICT, Office Supplies, other supplies and materials and equipment for official use of DENR-PENRO Capiz | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 25-10-2023 |  |  |  | 25-10-2023 | N/A | 27-10-2023 |  |  | 24-11-2023 | 24-11-2023 | Government of the Philippines (continuing budget) | 435795 | 435795 |  | 425753 | 425753 |  | 0.023043 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
| Labor and maintenance of office airconditioning unit of DENR PENRO Capiz | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 06-11-2023 |  |  |  | 06-11-2023 | N/A | 07-11-2023 |  |  | 24-11-2023 | N/A | Government of the Philippines (current year's budget) | 14600 | 14600 |  | 9700 | 9700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Catering services for the conduct of Orientation on VAWC and GAD related laws, rules and regulations. | Mary Grace Molina/PO II/OIC-Chief, Planning Section | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 23-11-2023 |  |  |  | 23-11-2023 | N/A | 28-11-2023 |  |  | 29-11-2023 | 29-11-2023 | Government of the Philippines (current year's budget) | 48000 | 48000 |  | 45000 | 45000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
| Catering services for the conduct of two (2) day catering services for the year-end assessment of physical and financial accomplishments for CY 2023 and presentation of the Implementation Plan of Programs, Projects and activities of DENR Capiz for CY 2024 on December 15-16, 2023, including venue, accomodation and visual facilities in the province of Capiz | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 12-12-2023 |  |  |  | 2023-12-12 | N/A | 13-12-2023 |  |  | 15,16-12-2023 | 19-12-2023 | Government of the Philippines (current year's budget) | 267500 | 267500 |  | 248750 | 248750 |  | 0.070093 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
-
-
-
-
-
-
-
-
-
-
-
[25 empty] | Total Allotted Budget of Procurement Activities | 3091810.75 | 3091810.75 | 0 |  |  |  | 15.57%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 2610523.5 | 2174118.5 | 436405
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 481287.25 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
-
-
-
-
| Repair and maintenance of office building of DENR PENRO Capiz (Hostel, COA Office, 2F Comfort Rooms) | Noemi C. Losbañes/PO III/OIC-Chief, Management Services Division | No | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23-11-2023 | 23-11-2024 | 23-11-2025 | 23-11-2026 | 23-11-2023 | N/A | 28-11-2023 |  |  |  |  | Government of the Philippines (current year's budget) | 49950 | 49950 |  | 49179.5 | 49179.5 |  | 0.015425 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
-
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 49950 | 49950 | 0 | 49179.5 | 49179.5 | 0 | 1.543%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | GEORLYN BEREBER | [9 empty] | PASCUAL I. ONGCO, JR. | [16 empty] | VICENTE A. SARDINA
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 248750
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 1
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 1 | 0 | 0 | -302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -273 | -273
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 16 | 0 | 0 | -13.1304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11.8696 | -136.5
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 1 | 0 | 0 | 0 | 0% |  | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 15 | 1 | 267500 | 248750 | 6.667% | 92.99% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 16 | 1 | 267500 | 267500 | 3.333% | 92.99% | 0 | 0
Total for Alternative Mode of Procurement | 15 | 1 | 267500 | 248750 | 6.667% | 92.99% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 15 | 93.75% | 3091810.75 | 98.41% | 2610523.5 | 98.15% | 0.15567
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 1 | 6.25% | 49950 | 1.59% | 49179.5 | 1.849% | 0.015425
Total | 16 | 100% | 3141760.75 | 100% | 2659703 | 100% | 0.15344
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 16 | 3141760.75
Total | 16 | 3141760.75
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell